## 04 Aug 21 (hidden)
SL # | Topics | DC | Points discussed | Action item | Action taken | Owner | ETA | Status
1 | Volume - Retype | ASH/ FPK | QOS not defined, inuse state volume is able to re type. Multiattach to Non Multiattach not able to do (vice versa). Multiattach log not enabled |  |  | Raghul / Pravin |  | Pending
3 | Migration from One Volume to Another Volume | FPK |  | Migration from One Volume to Another Volume | Pravin raised the ticket | Pravin |  | Pending
4 | MASAKARI Demo testing | ASH | Failover test | Pravin has to schedule a call to provide Demo to Murugan |  | Pravin |  | Pending
5 | Host Aggregation | ASH |  |  |  | Pravin |  | Pending
6 | DCI Temporarily configured | ASH/ FPK |  |  | Call scheduled on 05 Aug 21 | Gnana |  | Pending
7 | Using AWX Migration for Dupont | ASH/ FPK | Using AWX migration in Mgmt. Stack |  |  | Pravin/ Raghul/ Gnana |  | Pending
10 | CSI Hardening | ASH/ FPK | CIS Security Hardening :- Auditing , Using Script 92 we need run on ASH , for FPK Production we need put the Host maintenance Mode . | Hardening to be done | In Ashburn, script executed, 92% succeeded. Remaining failed which needs to be explored | Sriram |  | Pending
11 | Appformix | ASH/ FPK |  | Alert and Alarm Configuration for Network devices | SNMP trap configured and tested, Alarm is generating need to configured manually to all network devices. | Ugandhar |  | Pending
12 | SMTP / Graylog | ASH |  | Configuration to be done | SMTP configuration competed for Nagios/ Graylog still pending and Narinder is working on it | Ugandhar | 2021-08-06 | Pending
13 | RCA |  |  | Rajan has to follow the ticket | In remarks, ticket Moved to Engg team | Rajan |  | Pending
14 | Raghul - speak to Radha on intersite replication
15 | TCS Central Repository | ASH/ FPK | TCS Central Repository document has been prepared by Canonical and sent to TCS for Review | TCS should review and provide Feedback to Canonical | - | Pravin/ Sriram/ Arun |  | Pending
16 | New Server Build | ASH | All 16 servers racked, and ILO configured. | All 16 servers to be built |  | Pravin |  | Pending

## Summary
| AAAAA | AAAAA | AAAAA | AAAAA | AAAAA | AAAAA | AAAAA
Ageing (Days)
Count of SL #
Row Labels | 6 | 8 | 27 | 36 | 40 | 41 | 42 | 48 | Grand Total
Compute | 3 | 1 |  | 1 | 1 |  | 1 | 4 | 11
LMA | [5 empty] | 2 |  | 2 | 4
Network | [7 empty] | 2 | 2
Storage |  |  | 1 | [5 empty] | 1
Grand Total | 3 | 1 | 1 | 1 | 1 | 2 | 1 | 8 | 18

## Pending Items
SL # | Topics | Tower | DC | Action item | Severity | Action taken (History) | Action taken (Today's Progress) | Start Date | Today | Age | Owner | ETA | Actual Close date | Status
1 | IP reservation | Network |  | while we extend the networks to the physical devices it picks the ip address randomly, its creating a problem during migration ( as the IP’s will be already mapped for the server, like as-is). So needs to provide an feasibility to enable the ip address for the devices while extending |  | 11 Aug 21: It’s a future enhancement, may be its part of L3. It needs to be taken Nick 12 Aug 21: Ramprasad from Juniper had asked some time to look into the possibilities of incorporating this. 16 Aug 21: need to follow with Ramprasad 19 Aug 21: No update 23 Aug 21: No progress 24 Aug 21: No progress 31 Aug 21: Same status, no update from Juniper 07 Sep 21: it will be available in next release, not sure of the next release schedule. Looking for other workaround as well, Juniper will comeback and asked 2 or 3 days time. 13 Sep 21: Same status 20 Sep 21: Juniper Senthil has to comeback 24 Sep 21: No update from Juniper | 04 Oct 21: Code level change required, no confirmation from them on adding in the next level. Temp workaround will be given in next 2 days. 05 Oct 21: no response 18 Oct 21- no progress | 2021-08-04 | 2021-10-19 | 76 | Gnana |  |  | Pending
2 | CIS Hardening | Compute | ASH/ FPK | CIS Security Hardening :- Auditing , Using Script 92 we need run on ASH , for FPK Production we need put the Host maintenance Mode . Infra nodes Control nodes LMA nodes Need to document remaining issues | Critical | 09-Aug-2021 :-LMA , Compute Infra, Controller Nodes 12 Aug 21: LMA and Juju notes yet to be done 16 Aug 21: 2 Physical Nodes Pending (Rados Gateway) Virtual will be done one by one. 17 Aug 21: Storage side Physical Nodes completed, However Infra/ MASS nodes 02 and 03 are pending in Virtual: Contrail VMs LMA are under progress 19 Aug 21: Only MASS (2) and JUJU (3) pending, escalated but still in the same status. 20 Aug 21: No progress 24 Aug 21: Still MASS and JUJU pending waiting for Canonical to provide the steps (Upgrade and Backup Procedure) 31 Aug 21: No progress 07 Sep 21: No Progress 13 Sep 21: No Progress 24 Sep 21: Juju and MASS is still pending, both will be completed as soon as JUJU get fixed. Canonical is working on that. |  | 2021-08-04 | 2021-10-19 | 76 | Pravin |  |  | Pending
3 | Appformix | LMA | ASH/ FPK | Alert and Alarm Configuration for Network devices | Critical | SNMP trap configured and tested, Alarm is generating need to configured manually to all network devices.09-Aug-2021:- Awaiting for vendor input 17 Aug 21: No update 18 Aug 21: No Progress, waiting for Juniper to comeback 19 Aug 21: No progress 23 Aug 21: Waiting for PS to respond 24 Aug 21: Waiting for PS to respond 07 Sep 21: Waiting for PS team to respond 13 Sep 21: Waiting for PS team to respond 24 Sep 21: Working with PS team, call initiated today, we have given our requirements 27 Sep 21: Working with PS team. | 04 Oct 21: Its hold for sometime, its taken to Juniper Account team. 05 Oct 21: no progress | 2021-08-04 | 2021-10-19 | 76 | Ugandhar/ Gnana |  |  | Pending
4 | Migration from One Volume to Another Volume | Compute | FPK | Migration from One Volume to Another Volume |  | 09-Aug-2021 :-Escalated to Vendor , Rajan has to Send mail to vendor Raghul has to check with Vendor 16 Aug 21: support team has given input, we need to check internally and revert 17 Aug 21: Validated, to be coordinate with Dupont ops team and customer to get the Downtime. It has to be discussed with Murugan in the call Raghul - no impact on any application so we can run without informing Dupont Ops team and Customer. Pravin - has to check and confirm this on impact. Raghul will also check on Windows machines and update status with Pravin 19 Aug 21: Windows Machine deployed promoted as Domain controller, Raghul migrating the servers he will confirm today morning EST 24 Aug 21: Unable to power on VM, Arun has raised ticket. Still working with Canonical to sort it out 31 Aug 21: No Progress 07 Sep 21: To be checked with Raghul 13 Sep 21: To be checked with Raghul 21 Sep 21: windows 2016 and ubuntu 18.04 tested. waiting for the infra to continue test 24 Sep 21: Raghul prepared steps doc, and it requires downtime to perform the Migration and need to discuss with respective Stakeholders | 04 Oct 21: testing going on, results will be shared today to Murugan, Multiple OS yet to be done by this week. 06 Oct 21: will be shared today | 2021-08-04 | 2021-10-19 | 76 | Pravin/ Raghul |  |  | Pending
5 | Host Aggregation | Compute | ASH | Placements needs to be discussed |  | 09-Aug-2021 : Will Scheduled This Week 16 Aug 21: Call need to be scheduled this week 17 Aug 21:Yet to schedule a call 24 Aug 21: 6 nodes to be added, and its in the progress. Once all the 6 nodes added then Pravin will schedule a call before this week 31 Aug 21: No Progress 07 Sep 21: Pravin will schedule the call this week 13 Sep 21: Pravin will schedule by this week 21: Sep 21: Yet to be scheduled |  | 2021-08-04 | 2021-10-19 | 76 | Pravin/ Murugan |  |  | Pending
6 | MASAKARI Demo testing | Compute | ASH | Failover test Pravin has to schedule a call to provide Demo to Murugan |  | 09-Aug-2021:-Will Scheduled This Week 16 Aug 21: Call need to be scheduled this week 17 Aug 21: Yet to schedule a call 24 Aug 21: 6 nodes to be added, and its in the progress. Once all the 6 nodes added then Pravin will schedule a call before this week 31 Aug 21: No Progress 07 Sep 21: Pravin will schedule the call this week 13 Sep 21: Pravin will schedule by this week 21: Sep 21: Yet to be scheduled |  | 2021-08-04 | 2021-10-19 | 76 | Pravin |  |  | Pending
7 | Hardware Monitoring | LMA | ASH/ FPK | HP one view/ Super Micro servers Hardware monitoring to be enabled | Critical | 10 Aug 21: Fpk super micro servers configured. Ash is pending. For HP one view both sites pending Pravin has to provide access to HP OneView to deploy 17 Aug 21: vCenter access provided to Selva, he has to deploy HP One View and proceed further 18 Aug 21: Pravin will work on this today 19 Aug 21: VM created in vCenter, size 247 GB its hard to download and copy to KVM nodes. Downloaded latest version of HP One view (qcow) we are trying to deploy. 24 Aug 21: Super Micro Ashburn is still under progress and it will be completed today. HP One view: tried with new Qcow, same issue so we are trying reach out HP or will try deploy it on the Openstack and try 25 Aug 21: Hardware monitoring enabled for Franklin park & Ashburn storage nodes. If any hardware issues system will trigger the alert notification to alpha4.cloudsupport@tcs.com mail id. Pravin working with HPE team to fix HPE OneView KVM image issue. HPE servers hardware monitoring will be enabled once KVM image issue fixed. 31 Aug 21: No progress 07 Sep 21: Pravin will raise support case to HPE support team for KVM image issue. 13 Sep 21: Support case raised and chasing with team to get close. 21 Sep 21: Informed Vaibhav to check internally on the feasibility of supporting application on Ubuntu KVM. 24 Sep 21: yet to get response from Vaibhav | 04 Oct 21: will get update from Vaibhav today. 05 Oct 21: no reposnse 06 Oct 21: spoken with Shilash 08 Oct 21:Selva to Sent out communication today 19 Oct 21: HP Shaliash, has to confirm the temp workaround steps to run the Hardware Manitoring, for temp exsiting ESX host can be used, Selva can be used for this. | 2021-08-04 | 2021-10-19 | 76 | Selva/ Pravin |  |  | Pending
8 | Management Network Discussion | Network | ASH/ FPK | Slider to be prepared with Pictorial view and should call to be scheduled along with Murugan, Gnana and Pravin |  | 11 Aug 21: Call scheduled on Thursday 07:00 - 07:30 PM 16 Aug 21: InProgress 17 Aug 21: Decided to create separate tenant for ILO Management. Work in progress Pravin has to add host in the new tenant HP one view in VM ware env deployed, it needs to converted to work KVM (Qcow). Pravin will work on this. 18 Aug 21: Network to be created, Jump server to be put. Resource shortage. Contrail Error to be sort it out. 23 Aug 21: Contrail Error to be sort it out. 24 Aug 21: Pravin checking the possibilities of incorporating AD 31 Aug 21: Workaround yet to be provided for Contrail Agent Error in Ashburn, once contrail agent error fixed, then Pravin will create host to facilitate the same. 07 Sep 21: Pravin has creating a separate aggregates for shared tenant, he will create by today or tomorrow and then compute host and the same aggregates. 13 Sep 21: Aggregates created, Host added, then working on access for internal team. Service Request to be raised to get access. 21 Sep 21: VM to be created and provide access to the support team. Will be completed by this week. 24 Sep 21: Pravin is working on it. Trying to complete it by 24 Sep 21. | 04 Oct 21: Grps getting created, then access to be given 06 Oct 21: Ops team have to give Confirmation on competelin of Grp creation | 2021-08-04 | 2021-10-19 | 76 | Gnana/ Pravin |  |  | Pending
9 | AMD Discussion | Compute | ASH/ FPK | Pravin has to speak with AMD Compute Nodes for POC |  | 16 Aug 21: Yet to get the nodes (BPM) details from the AMD Vendor (BOM) 17 Aug 21: No Progress 18 Aug 21: Waiting for vendor to response 24 Aug 21: Waiting for vendor to response 31 Aug 21: No Progress 07 Sep 21: yet to get the BOM 13 Sep 21: No progress 21 Sep 21: Yet to get the details, need to follow up with Murugan 24 Sep 21: Yet to receive. | 04 Oct 21: - | 2021-08-10 | 2021-10-19 | 70 | Pravin |  |  | Pending
10 | Grafana Dashboard | LMA | FPK | Need to configure similar to Ashburn in Fpk |  | 17 Aug 21 - No Progress 20 Aug 21: Working with Raghul to configure Grafana dashboard as similar to Ashburn 24 Aug 21: working with Raghul, Ugi will complete it by this week. 31 Aug 21: Raghul ye to be come back on the validating dashboard. 07 Sep 21: Still Raghul is working on it. 13 Sep 21: Ugi will follow up with Raghul on the progress 24 Sep 21: No progress 27 Sep 21: Need to work with Raghul | 04 Oct 21: last week, need to connect with Raghul. 06 Oct 21: Need to be discussed with Raghul 18 Oct 21 - | 2021-08-11 | 2021-10-19 | 69 | Ugandhar |  |  | Pending
11 | SIEM and VA | Compute | Ash | SIEM and VA need to be configured in Ashburn |  | SIEM and VA need to be configured in Ashburn, network trouble shooting Friday got completed. Pravin has to follow up with Security team to complete. 17 Aug 21: SIEM: Configured by security team, sent Canonical to configure the change, if Narinder unable to do it we ill compete it today VA: Inventory to be shared with Security team today SIEM: Narinder configured the change, he confirmed. we informed security team to validate and confirm VA: No progress 31 Aug 21: SIEM: Inventory to be shared with Security team VA: Inventory to be shared with Security team 07 Sep 21: no progress 13 Sep 21: Pravin will working on this and will Send the inventory by today. 21 Sep 21: For SIEM: Inventory shared. Provided the non working nodes, we are checking on the issue and will reconfigure the syslog configuration. Arun will completed today. 24 Sep 21: Completed, Windows 8 machines are pending. For VA: Team shared the non working nodes on the VA, team working on the issue. 24 Sep 21: AD authentication is not working in Non Working nodes, still we are trying fix the issue. | 05 Oct 21: No progress 06 Oct 21: No Progress 11 Oct 21: wotking on it, will be completed today 18 Oct 21: try to complete it by this week | 2021-08-16 | 2021-10-19 | 64 | Pravin |  |  | Pending
12 | 16 servers to be commissioned in Fpk environment | Compute | Fpk | 16 servers to be commissioned in Ash environment |  | 18 Aug 21: SFP shortage, fabric connectivity issue, it needs to be discussed with Data center team We able to connect 10 servers and 6 are pending. Those 10 servers we have asked 5 in Type 1 and 5 in Type 3. But team have done incorrectly and we have asked the team to correct it 24 Aug 21: Pravin has to follow up with Yash on completing the Cabling. Tamil will add 5 serves today 31 Aug 21: No progress 07 Sep 21: 13 nodes completed, 1 Node has RAM issue and ticket to be raised. 2 nodes has cabling issue. 13 Sep 21: Same Status 21 Sep 21: Informed Selva to raise a case, he will raise today | 06 Oct 21: chasing with DC team 07 Oct 21: Walli is chasing with team on DC visit 11 Oct 21: Adapter issue got solved, 1 Cable issue and RAM issue is pending 19 Oct 21: RAM issue and Proicessor issuie going on. | 2021-08-12 | 2021-10-19 | 68 | Pravin |  |  | Pending
13 | The monitoring of pool utilization and OSD utilization | Storage |  | Have the monitoring of pool utilization and OSD utilization to be streamlined to avoid the problem we faced today in Pre-prod. | Critical | 31 Aug 21: mail sent to canonical team to get the information 07 Sep 21: Canonical yet to respond 13 Sep 21: Canonical responded, request has to validate in the JUJU config file. Arun/ Pravin will work on this today. 21 Sep 21: No Progress, Ugi will follow up with Arun to get completed 24 Sep 21: Monitoring threshold for the storage alert configured in both DCs, Once again it should be revalidated by UGI. To be completed by 29 Sep 21. 27 Sep 21: Same Status | 07 Oct 21: Validation to be done 18 Oct 21 - Validation to be done | 2021-08-25 | 2021-10-19 | 55 | Ugandhar |  |  | Pending
14 | Pre Prod Decommissioning | Compute | Ash |  |  | Migration still going on, DC and few internal server pending, team is working on it |  | 2021-09-13 | 2021-10-19 | 36 | Pravin |  |  | Pending
15 | TCS ECP domain access should be created for all | Compute |  |  |  | 24 Sep 21: PASS team shared the user IDs, Solutions team need to get details to create the IDs 27 Sep 21: Same Status |  | 2021-09-15 | 2021-10-19 | 34 | Ugandhar |  |  | Pending
16 | PASS and Tools Migration to be completed by this weekend or early next week | Compute |  |  |  | 21 Sep 21: Tenant creation network creation done, we need to co ordinate with Monitoring and Pass team to do the Migration. Replication starting today | 04 Oct 21: Monitoring team requires Downtime to be scheduled. PASS team access to be given once grp created PASS team: Grp created, access given, comm to be sent out Monitoring: Will close it by today or tomorrow | 2021-09-15 | 2021-10-19 | 34 | Pravin |  |  | Pending
17 | Private Flavors is that possible? | Compute |  |  |  | Pravin has to explore on Private Flavors and applicability and update Murugan 21 Sep 21: Aggregates to be created based on upcoming customer discussions |  | 2021-09-15 | 2021-10-19 | 34 | Pravin |  |  | Pending
18 | Extension of Boot volume |  |  |  |  | Volume extension needs to be tested in all OS types. 24 Sep 21: Pravin and Raghul has to discuss with Murugan on this Monday |  | 2021-09-21 | 2021-10-19 | 28 | Pravin/ Raghul |  |  | Pending

## Sheet1 (hidden)
11 | RPC - Package (CSI Hardening) | Compute | ASH/ FPK | 16 Aug 21: Still exploring to understand what are all nodes we required for RPC 17 Aug 21: No Progress 18 Aug 21: No progress 24 Aug 21: No progress 31 Aug 21: No progress | 2021-09-13 21:00 | 2021-08-04 | 2021-10-19 | 76 | Pravin | Completed

## Completed
SL # | Topics | DC | Points discussed | Action item | Action taken | Owner | ETA | [5 empty] | Status
7 | Graylog | ASH |  | Reverse Proxy configuration to be done, Narinder will work and update on Friday | 09-Aug-2021:- Https- completed, Awating for Firewall port to be opened 10 Aug 21- Configured. | Arun/ Ugandhar | [6 empty] | Completed
10 | Arun has to provide VM to Gnana |  |  | Arun has to provide VM to Gnana | 09-Aug-2021:- Provided Virtual machines | Arun/ Pravin | [6 empty] | Completed
1 | Volume - Retype | ASH/ FPK | QOS not defined, inuse state volume is able to re type. Multiattach to Non Multiattach not able to do (vice versa). Multiattach log not enabled |  | 09-Aug-2021 :-Multi attach Volume type to Non Multiattach type is not possible. | Raghul / Pravin | [6 empty] | Completed
1 | FMC Console |  | its not switched off, not reachable its in the pause state | Need to explore the issue | 09-Aug-2021 :-No Progress 11 Aug 21: No logs available, it will be investigated if occurs again | Gnana/ Sriram | [6 empty] | Completed
23 | Storage to be increased in Ashburn | Compute | Ash |  |  | Storage to be increased in Ashburn | Done | 2021-08-16 | 2021-10-19 | 64 | Pravin |  | Completed
14 | S NAT | Network | ASH/ FPK | For Dupont S NAT is not required. | S NAT Configuration | Ticket has been raised, it might fixed today/tomorrow 12 Aug 21: JTAC - Ashish came and collected the Logs and he will come back to us with the solution 16 Aug 21: still in progress 17 Aug 21: Automatically problem got solved, however to fix the issue permanently we need to wait for this issue to reoccur |  | 2021-08-04 | 2021-10-19 | 76 | Gnana/ Vishwa |  | Completed
6 | Storage Performance Testing | Storage |  | There is an issue in script (Woodpecker)which Radha has to come back on the issue | 09 Aug 21: Requesting Raghul to connect with Radha on this. 11 Aug 21: Ash completed, Fpk is pending 17 Aug 21: No update | 20 Aug 21: no need to do for Fpk | 2021-08-04 | 2021-10-19 | 76 | Radha |  | Completed
24 | Received RCA from Account team and action to be taken from Engg Team |  |  | drafting the initial RCA for the issue occurred today |  |  |  | 2021-08-25 | 2021-10-19 | 55 | Radha and Compute team |  | Completed
10 | Raghul - speak to Radha on multi attach type volume Migration | Storage | ASH/ FPK |  |  | 09-Aug-2021 : Raghul has to follow up with Radha 10 Aug 21: LXD Containers , public API Access to be enabled , Documentation has to reviewed and sign off by Radha. 17 Aug 21: |  | 2021-08-04 | 2021-10-19 | 76 | Raghul / Radha |  | Completed
3 | Migration using AWX | Compute |  | Call needs to be set up along with Murugan and Vinodh |  | 09-Aug-2021 :-Discussion Happened , pending with Vinod to get confirmation from Customer for Security Approval 16 Aug 21: No update, 17 Aug 21: Tenant to be created, need to check with Murugan 18 Aug 21: Resources Shortage in Pre Prod 19 Aug 21: still in the same status 20 Aug 21: No update | 24 Aug 21: Waiting for Pre Prod migration to be completed to get the resources. 31 Aug 21: No progress 07 Sep 21: Firewall Port opened between AWX server to our mgmt end, completed the automation testing for Migration. Ashburn completed, FPK they are working team | 2021-08-04 | 2021-09-07 | 34 | Pravin |  | Completed
6 | TCS Central Repository | Compute | ASH/ FPK | TCS Central Repository document has been prepared by Canonical and sent to TCS for Review TCS should review and provide Feedback to Canonical |  | 09-Aug-2021:-Reviewed and sign off ,Required Holistic representation Block Diagram From Narinder. Further it has to be reviewed by Compute Team 12 Aug 21: it will be done today 16 Aug 21: VM Provided to Narinder to work on, further status will be provided by Narinder today 17 Aug 21: No update from Narinder 19 Aug 21: Need to discuss internally and provide required resource to proceed deployment further. | 24 Aug 21: Canonical working on creating main Repository in ASH. One host can be given from Zone one Pravin will provide it to Canonical by this week 31 Aug 21: No Progress 07 Sep 21: provided the repository server in Ashburn, canonical working on it | 2021-08-04 | 2021-09-07 | 34 | Pravin/ Sriram/ Arun |  | Completed
16 | Contrail Agent | Network | FPK | in error state in Fpk | Critical | Ticket raised, solution has been provided 12 Aug 21: Solution has been given by JTAC and it needs to be implemented by our Openstack Team 16 Aug 21: It will be done by today/ Tomorrow 17 Aug 21:CR has been raised by Sriram, and it will be discussed and in the call and approved by Murugan for proceed. Vendor recommended to test it in Pre Prod, then in the Prod Env. 18 Aug 21. Vendor recommended to test it in Pre Prod, then in the Prod Env. Vendor provided few steps and it needs to be validate in our env and then we need to decide on the CR execution and down time requirement. CR has been raised by Sriram, and it will be discussed and in the call and approved by Murugan for proceed 23 Aug 21: No update 24 Aug 21: Waiting for Ashburn issue to be fixed. Need to see the other possibilities to incorporate the steps which vendor provided | 31 Aug 21: Workaround provided , need to test and confirm in another non critical environement. Since Ashburn also in the issue, we need to wait for Ashburn to get fixed. 07 Sep 21: Completed | 2021-08-11 | 2021-09-07 | 27 | Gnana/ Pravin | 2021-09-03 | Completed
22 | Contrail Agent Error (Blocked State) | Network | Ash | Contrail Agent error identified in Ashburn |  | 23 Aug 21: No update 24 Aug 21: Working in progress 25 Aug 21: Log provided to explore the issue | 31 Aug 21: Workaround yet to be provided for Contrail Agent Error in Ashburn 07 Sep 21: Completed | 2021-08-19 | 2021-09-07 | 19 | Gnana/ Vishwa | 2021-09-03 | Completed
6 | RCA | Compute |  | Rajan has to follow the ticket |  | In remarks, ticket Moved to Engg team 09-Aug-2021:- Assigned to Specific Engineer(Tiago) 10 Aug 21: Update received from Tiago, Rajan will update the status in the call. 12 Aug 21: Still discussion going up and down, yet to receive the RCA. 17 Aug 21: Vendor RCA concluded, Rajan has to schedule a call to explain the RCA | 31 Aug 21: Yet to be scheduled | 2021-08-04 | 2021-10-19 | 76 | Rajan |  | x
16 | Migration to Coriallis | Compute | Ash | Migration to Coriallis |  | Data migration link connectivity to be finalized Coriallis - waiting for VM deployment Coriallis License to be followed up 17 Aug 21: Network created by Gnana, Pravin working on deploying VM then we will send vendor to get license 17 Aug 21: Network created by Gnana, Pravin working on deploying VM then we will send vendor to get license 18 Aug 21: VM created, and Requested for License, Legal pending. 19 Aug 21: Temp license provided for testing purpose, Network team working on pre prod connectivity on Coriallis appliance to Pre-prod. Then migration and the validation to be done. 24 Aug 21: Coriolis to Ceph Mon Pending - Pravin will work on this today 31 Aug 21: Pravin is working on this. 07 Sep 21: completed, started using the tool. |  | 2021-08-16 | 2021-10-19 | 64 | Pravin |  | Completed
6 | New Server Build | Compute | ASH | All 16 servers racked, and ILO configured. All 16 servers to be built |  | Deployment and pre requisite installation in progress 16 Aug 21: Completed 17 Aug 21: Unable to create VM contrail Error, CR raised 19 Aug 21: Its in same status. Network team is working on it. Working with Contrail 24 Aug 21: Still the issue continues, trouble shooting going on 31 Aug 21: No porgress 07 Sep 21: build completed for 10 Nodes, we will add the new host into aggregates based on the utilization. Remaining 6 nodes, team is working on it and will be completed tomorrow | 13 Sep 21: Completed | 2021-08-04 | 2021-10-19 | 76 | Pravin |  | Completed
1 | DCI configuration | Network |  | its completed, few issues which may affect day to day activities (end users), teething issues there` | Critical | 12 Aug 21: Escalated till Nick, solution yet to arrive. Call with Juniper is going on. 16 Aug 21: Solution received, review in progress 17 Aug 21: Working fine, Testing done in Dummy network. configuration to be done in Actual network. need to be discussed in the daily call for the further course of action 18 Aug 21: Maintenance was scheduled, But Unable to perform the maintenance activity due to technical issue 19 Aug 21: Team is working with Juniper, in progress 20 Aug 21: Team is working with Juniper, in progress 23 Aug 21: Still pending with Juniper, DCI configuration almost over, there is a route failover not happening, Juniper is trying find the issue, Uma Shankar Murugan following with them. 24 Aug 21: yet to be fixed the HA failover, Uma Shankar Murugan is working with Juniper 27 Aug 21: yet to be fixed the HA failover, Uma Shankar Murugan is working with Juniper 31 Aug 21: HA is working now,workaround given,further testing in progress. 07 Sep 21: Rerouting to be done and planned on this weekend. 13 Sep 21: Rerouting to be done and planned on last weekend. However it was reshcduled tomorrow/ Day after tomorrow IST , if Secondary Inter DC link up. 17 Sep 21: planned on this weekend | 20 Sep 21: Completed | 2021-08-04 | 2021-10-19 | 76 | Gnana |  | Completed
16 | Draft CIS Hardening Post Cloud Deployment document | Compute | ASH/ FPK | Draft to be reviewed and respond back to Liz |  |  |  | 2021-08-25 | 2021-10-19 | 55 | Compute team |  | Pending
12.0784 | Graylog | LMA | FPK | Log Rotation need to configure similar to Ashburn |  | Graylog retention policy based on size rather than days 17 Aug 21: No Progress 20 Aug 21: Working with Pravin, possibly Monday we can close this 23 Aug 21: sent a mail to Arun / Sriram/ Pravin to configure the Graylog configuration as per Narinder. Waiting for their update 24 Aug 21: Pravin will complete the activity before EOD 25 Aug 21. Ugi will complete this before this week. 31 Aug 21: Yet to be completed. 07 Sep 21: Pravin has to complete activity. 13 Sep 21: Pravin will work on this today. | 24 Sep 21: Completed | 2021-08-11 | 2021-10-19 | 69 | Ugandhar |  | Completed